## Predni
| Project | Prednisolone ophthalmic suspension 1%
| Market | US
| Client | Genepharm
| RLD | Pred Forte
| Packs | LDPE plastic bottles with droppers
| API | Axplora
| Upcoming milestone | 3M stability of prototype batch- Completed. Tech transfer to CMO
| Updated on | 2024-09-14
| Milestone | Timeline (Plan) | Timeline (Revised) | Timeline (Actual)
| T0 | 2023-07-01 | completed | completed
| Prototype completion (Method Dev. + Loading) | 2024-03-01 | completed | completed
| Prototype completion (3M) | 2024-06-01 | 2024-06-01
| Pilot BE completion | NA | NA
| Scale-up Batch | 2024-12-01 | 2024-12-01
| EB Loading | 2025-05-01 | 2025-05-01
| EB Stability (6M) | 2025-11-01 | 2025-11-01
| Filing | 2025-12-01 | 2025-12-01
Action No | Action | Team | Progress | Target Date for completion | Actual Completion Date | Remarks
CRITICAL ACTION POINTS
1 | CMO Finalization | PMT | In progress | 2024-10-01 |  | Audit report available from GSA QP. Discussion on findings by QP will be done on 04.10
2 | QbD batches | FRD | Completed | 2024-05-20 |  | Only Compatibility Studies Completed Repeat compatibility studies
3 | API availability (500 gms) | Purchase | Completed | May end / 1st week June-24 |  | Received
4 | PSD Data for new batch | FRD | Completed
5 | Compatibility batches Analysis | ARD | Completed | 2024-06-24 |  | Analysis started on 14-June-24 Assay & BKC Analysis completed RS Analysis- Completed
6 | Reproducible Batches-(Dissolution Pending) | ARD | Completed | 16/08/2024 23-Aug-24 |  | Disso analysis for reproducible batches ongoing
7 | Client Query Response | ARD/FRD | Completed | 20/06/2024 25-June-24 |  | Shared response on 11 July 24
9 | PDE | FRD | Completed |  |  | Shared with CMO
10 | IPR clearance | FRD | Completed | 22/07/2024 03-Aug-24 |  | Details shared to IPR Confirmation from IP expected till 03-Aug-24
11 | PDR | FRD | In progress | 2024-08-30 |  | Assay Data release pending from ARD-20-Sep-24-ARD will confirm:BKC plan on 25-Sep, Assay plan :26-Sep-24 Data release by 03-Oct-24, PDR by 05-Oct-24
12 | 6M data release | ARD | Completed | 27/07/2024 03-Aug-24
13 | Over all project presentation | FRD | Completed | 2024-08-01 | 2024-08-14
14 | Over all project presentation | FRD | Completed | 2024-09-30
16 | Unknown Impurity conclusion | ARD | Completed | 2024-08-20 |  | Discussion completed, repeat analysis will be perform along with Photo stability samples
17 | Dissolution Method Report for Filling to be check | ARD | Completed | 2024-08-27 |  | Disso data to be check Discuss & confirm-completed
12 | Tech Pack sharing | PMT | In progress | 2024-10-01 |  | Requested checklist from Bora on 24.09
13 | Buffer Capacity | ARD | In progress | 2024-09-28 |  | STP sign off by 28-Sep-24(Data to QA 26-Sep-24)-Not yet done Analysis Plan from 30-sep-24
14 | Partical size verification(vimata lab) | ARD | In progress | 2024-10-01
PROTOTYPE DEVELOPMENT STAGE
1 | PDS | ARD | Completed | 2023-08-21
2 | RLD availability- Pred Forte | BD | Completed | 2023-08-10
4 | Q1Q2 sameness approval - Omnipred | RA | Completed
5 | Reverse Engineering | ARD | Completed
6 | Samples for method development | FRD | Completed | 2023-07-26
7 | Tentative analytical method development completion | ARD | Completed
| 7.1 Assay | ARD | Completed
| 7.2 Related Substance | ARD | Completed | 2023-09-22
| 7.3 Dissolution | ARD | Completed | 2023-10-05
| 7.4 PSD | ARD | Completed | 2023-08-02 | 2024-04-01
| 7.5 Soluble prednisolone | ARD | Completed
| 7.6 Viscosity | ARD | Completed
| 7.7 Osmolarity | ARD | Completed
| 7.8 Surface tension | ARD | Completed | 2023-09-23
| 7.9 BKC | ARD | Completed | 2023-09-25
8 | STP / MDR preparation | ARD | Completed
9 | STP / MDR Approval | DQA | Completed | 2023-09-30
10 | RLD Characterization | ARD/FRD | Completed | 2023-10-15
| RLD Characterization (Omnipred) | ARD/FRD | Completed
11 | Initial stability batches initiation | FRD | Completed | 2023-08-18
12 | Particle size reduction process optimization | FRD | Completed | 2023-12-30
13 | IIG clearance | FRD | Completed | 2023-08-30
14 | Characterization of test & reference as per BE recommendation | ARD/FRD | Completed | 2023-12-30
15 | 1M Stability samples | FRD | Completed | 2023-09-25
16 | 1M Stability analysis completion | ARD | Completed | 2023-10-14
17 | Trade dress finalisation | FRD | Completed | 2023-08-30
18 | Prototype Stability Initiation | FRD | Completed | 2024-01-16
19 | Prototype development with 1 M stability | FRD | Completed | 2024-02-25 | 2024-04-01
20 | Final Stability Data 3M | FRD | Completed | 2024-04-25 | 2024-05-29
21 | Final Stability Data 6M | FRD | Completed | 2024-07-24 | 2024-08-05 | 6M Anlaysis- Completed (Except Dissolution) Repeat RS data rls pndng
23 | Product Development Report Signoff | FRD | In progress | 2024-08-08 | 2024-09-01 | PDR will be completed by 2nd week of Sep
24 | TT Package Readiness | All | Not Started
READY FOR SCALE UP
1
2
3
4
5
6
7
8
9
10
11
12
13
ALL
ARD
FRD
DQA
IP
PMT
RA
N32
Purchase
BD
ARD/FRD
CLIENT
Formulas:
Timeline (Actual) = [Timeline (Actual), row above]+40