## solid oral
| Project | Zonisamide Capsule 150mg,200mg,300mg | [6 empty] | Not Started
| Market | US | [6 empty] | In progress
| Client | Genepharm | [6 empty] | Completed
| RLD | ZONEGRAN
| Packs | 100 capsule in 1 BOTTLE
| API | Maithri drugs/Glenmark
| Upcoming milestone | T0 Completion
| Updated on | 2024-09-14
| Milestone | Timeline (Plan) | Timeline (Revisedl) | Timeline (Actual)
| T0 | 2024-08-01 | 2024-08-01 | 2024-08-01
| Prototype completion (Method Dev. + Loading) | 2024-10-01 | 2024-12-01
| Prototype completion (3M) | 2025-01-01 | 2025-03-01
| Pilot BE completion | 2025-02-01 | 2025-02-01
| Scale-up Batch | 2025-05-01 | 2025-05-01
| EB Loading | 2025-05-01 | 2025-05-01
| EB Stability (6M) | 2025-11-01 | 2025-11-01
| Filing | 2025-12-01 | 2025-12-01
Action No | Action | Team | Progress | Target Date for completion | Latest Date for completion | Actual Completion Date | Remarks
SEPTEMBER ACTIVITY
1 | Analytical method development | ARD | In progress | 2024-09-01 |  |  | Disso Repot Sign off Assay Analysis cmpleted RS analysis completed
2 | Preformulation studies | FRD | In progress | 2024-10-01 |  |  | Loading completed , Analysis Ongoing
3 | Preliminary stability loading | FRD | In progress | 2024-10-01 |  |  | Analysis Ongoing
4 | Additional API procurement (with particle size Between 200 -250 μm, Qty: 1.0 kg) | PMT | In progress | 2024-10-01 |  |  | PO shared to supplier on 27-Sep, Purchase will confirm receipt date on 30-sep-24
5 | Arrange quotes from Axis for pilot & pivotal BE | CLINICAL | In progress | 2024-10-01
6 | O-DMF Review- Maithri | ARD | Not Started | 2024-10-01 |  |  | To be Plan
T0 ACTIVITY
1 | PAF signing | PMT | Completed | 2024-06-14 | 2024-08-30 | 2024-06-14 | PAF revised
2 | API source identification | BD | Completed | 2024-06-15 |  | 2024-06-18
3 | Availability of CoA, PSD data, CEP / DMF information | BD | Completed | 2024-06-23 |  | 2024-06-19
4 | Quotation from API supplier | BD | Completed | 2024-06-26 |  | 2024-06-19
5 | CDA Execution with API supplier | BD | Completed | 2024-07-05 |  | 2024-08-23 | Both Glenmark and Maithri signed
6 | Availability of open part DMF | BD | Completed | 2024-07-09 |  | 2024-06-29 | Glenmark ODMF available. Maithri DMF received on 29-Aug-24
7 | Finalization of API source | BD | Completed | 2024-07-12 |  | 2024-06-28 | Glenmark
8 | Availability of T&A License | DQA | Completed | 2024-07-24 |  | 2024-07-22
9 | Availability of import license (RLD) | DQA | Completed | 2024-08-09 |  | 2024-08-01
10 | Availability of import license (API) | NA | NA | NA
11 | IP Landscape by V-Ensure | IPM | Completed | 2024-07-24 |  |  | Shared to FRD on 26-Jul-24
12 | Formulation Development strategy | FRD | Completed | 2024-07-23
13 | Analytical method development strategy | ARD | Completed | 2024-07-23
14 | RA Strategy | RA |  | 2024-07-23
15 | Procurement of innovator samples (RLD) | BD | Completed | 2024-08-30 |  | 2024-08-30 | Received
16 | Procurement of API | Purchase | Completed | 2024-08-22 |  | 2024-09-02 | Will receive on 02-Sep-24
17 | Procurement of raw material | Purchase | Completed | 2024-08-21
18 | Procurement of packing material | Purchase | Completed | 2024-08-21
19 | Procurement of columns, standards, impurities (Parallel) | Purchase | Completed | 2024-08-21 |  | 2024-08-13 | All impurities and columns available
20 | StageGate 0 Completion | PMT
PROTOTYPE DEVELOPMENT STAGE
1 | PDS | ARD | Completed | 2024-08-26 | 2024-08-26
2 | Samples for method development | FRD | Completed
3 | Analytical method development | ARD
| 3.1 Assay | ARD | Completed | 2024-09-10 | 2024-09-04
| 3.2 Related Substance(RS,Robtness,FD) | ARD | Completed | 2024-09-30
| 3.3 Dissolution | ARD | Completed | 2024-08-30 | 2024-08-28 |  | Analysis completed on 28-Aug-24
4 | MDR | ARD
| 4.1 Assay | ARD | In progress | 16 Sep 24 |  |  | MDR will signoff on 24-Sep-24 30-Sep-24
| 4.2 Related Substance | ARD | In progress | 2024-10-07 |  |  | MDR will signoff on 03-Oct-24
| 4.3 Dissolution | ARD | Completed | 2024-09-03
5 | STP | ARD
| 5.1 Assay | DQA | In progress | 2024-09-18 |  |  | STP will signoff on 24-Sep-24 30-Sep-24
| 5.2 Related Substance | DQA | In progress | 2024-10-11 |  |  | MDR will signoff on 03-Oct-24
| 5.3 Dissolution | DQA | Completed | 2024-09-03
| API Characterization (Physical and minimum Chemical Analysis) | FRD | In progress | 2024-09-01 |  |  | Physical Characterization completed
6 | RLD Characterization (Physical and minimum Chemical Analysis) | FRD | In progress | 2024-09-01 |  |  | Physical Characterization completed
7 | Preformulation Study data (Solubility and DECS) | FRD | In progress | 2024-09-01 |  |  | Preformulation Loaded Analysis Pending
8 | Initial stability batches initiation (1st) | FRD | In progress | 2024-09-01
9 | Multimedia Dissolution Matching / Discrimination Method Development Report Sign Off | FRD | In progress | 2024-10-01
10 | Tooling finalization | FRD |  | 2024-10-01
11 | Breakability study | FRD |  | NA
13 | Dissolution comparison with bio strength | FRD |  | 2024-10-01
14 | IIG clearance | FRD |  | 2024-09-01
15 | IP Clearance | IPM |  | 2024-10-01
16 | Trade dress finalisation | FRD |  | 2024-10-01
17 | Final Stability Initiation | ARD |  | 2024-10-15 |  |  | IP clearance, MMD, methods
18 | Final Stability batch initial analysis | ARD |  | 2024-10-15
19 | Final development with 1 M stability | FRD |  | 2024-11-24
20 | Final Stability Data 3M/6M | FRD |  | 2025-01-23
21 | FINAL FORMULA AND PROCESS FOR IP CLEARANCE (PILOT STAGE) |  |  | 2025-04-01
READY FOR PILOT BE
1 | BE center finalization & protocol initiation |  |  | 2024-12-01
2 | BE NOC & RLD license application & receipt |  |  | 2025-01-23 |  |  | To initiate BE NOC application based on 1M stability of prototype
3 | VSRs of Pilot BE Proposed Composition and docs upload in Provision Software |  |  | 2024-12-01
4 | Biowaiver |  |  | 2024-12-01
5 | RLD procurement for Pilot & Pivotal BE |  |  | 2024-12-01
6 | Elemental Impurity Assessment for final formula |  |  | 2024-12-01
7 | Nitrosomine of final formula |  |  | 2024-12-01
8 | 10-15 Pager Development Report to Justify about the selection of manufacturing process and How you arraived at the Pilot BE Compsosition |  |  | 2024-12-01
9 | QbD/ OFAT Design Finalization (for Process Optimization Batches relavant to Pilot Bio Formula, as a minimum Requirements) |  |  | 2024-12-01
10 | QbD/ OFAT Trials Complition (for Process Optimization Batches relavant to Pilot Bio Formula, as a minimum Requirements) |  |  | 2024-12-01
11 | IP Clearance sign off Before Pilot BE Studies |  |  | 2025-01-01
12 | Stage Gate - 2 Presentation (Permission for Pilot Bio Initiation or Skip) (PPT sign Off)
13 | Batch manufacturing for pilot BE |  |  | 2025-01-01
14 | Sample availability at BE center (Pilot BE) |  |  | 2025-01-01
15 | Successful Pilot BE Studies completion |  |  | 2025-02-01
AMV, SCALE-UP, EB & PIVOTAL BE
1 | Sending Samples for Method validation (Post Pilot BE Clearance) Justification Note if samples given for AMV, Before Pilot BE Clearance |  |  | 2025-03-01
2 | TT Documents Draft Readiness as per FRD TT Checklist | FRD |  | 2025-03-01
3 | TT Documents Draft Readiness as per FRD TT Checklist | ARD |  | 2025-03-01
4 | QbD Protocol Sign Off |  |  | 2025-03-01
5 | QbD Studies Completion and Report Sign Off |  |  | 2025-03-01
6 | API , excipient method feasibility |  |  | 2025-03-01
7 | Interim PDR upto Section 2.3.4 (Updated risk Assessment of the Manufacturing Process, Lab Scale and Updated Stability, Photostability and XRD Data for PDR, Review and Sign Off) Rest of the Points As Blank Template |  |  | 2025-03-01
8 | Method validation Protocol preparation |  |  | 2025-03-01
9 | Method feasibility & AMV requirement procurment |  |  | 2025-03-01
10 | AMV Initiation |  |  | 2025-03-01
11 | AMV completion |  |  | 2025-04-01
12 | Scale-up batch manufacturing |  |  | 2025-04-01
13 | Scale-up report signoff |  |  | 2025-04-01
14 | Stage Gate - IV PPT (Permission For taking Exhibit Batch)
15 | Exhibit batch manufacturing |  |  | 2025-05-01
16 | Exhibit batch stability loading |  |  | 2025-05-15
17 | Identification of CRO for Pivotal BE studies |  |  | 2025-04-01
18 | Getting quotation and Design Finalization (Pivotal) |  |  | 2025-04-01
19 | Pivotal BE NOC Application filling |  |  | 2025-05-01
20 | Pivotal BE NOC Availability |  |  | 2025-07-01
21 | RLD Procurement Completion for Pivotal BE |  |  | 2025-05-01
22 | Exhibit Batch Stability Data review upto 2M (Minimum before Pivotal BE) |  |  | 2025-08-08
23 | Pivotal BE initiation |  |  | 2025-08-01
24 | Successful Pivotal BE Studies completion |  |  | 2025-10-10
25 | 6M Stability of EB |  |  | 2025-11-17
26 | PDR Signoff |  |  | 2025-08-23
27 | Product Filing |  |  | 2025-12-17
28 | Deficency Queries and Approval Stage
ALL
ARD
FRD
DQA
IP
PMT
RA
N32
Purchase
BD
ARD/FRD
CLIENT
Formulas:
Timeline (Actual) = [Timeline (Actual), row above]+70